## Overview
Sip Studies - UAT Overview
Document | Sip Studies - UAT Test Plan
Generated | 2026-02-28 23:21
Scope | Current implemented front-end across Sip Studios, Ai RnD, Somm Support, and hash routing.
Build Type | Manual UAT - Functional/UI/Regression/Accessibility
Execution Status | Use UAT Cases sheet to execute and update Status, Actual Result, and Defect ID.
Status Legend | Not Run, Pass, Fail, Blocked, N/A
Priority Legend | P1 = High, P2 = Medium, P3 = Low
Live Metrics
Total Test Cases
Pass
Fail
Blocked
Not Run
Pass Rate

## UAT Cases
Test ID | Area | Feature | User Role | Preconditions | Test Type | Priority | Test Steps | Expected Result | Status | Actual Result | Defect ID | Notes
UAT-NAV-001 | Global Navigation | Brand House Tier Switch | Guest/User | Application loads successfully | Functional | P1 | 1. Open home page. 2. Click Ai RnD logo. 3. Click Somm Support logo. 4. Click Sip Studios logo. | Each logo switches brand tier and shows the corresponding sub-navigation and content page. | Not Run
UAT-NAV-002 | Global Navigation | Sip Studios Tabs Visibility | Guest/User | Brand tier set to Sip Studios | UI | P1 | 1. Select Sip Studios tier. 2. Review visible tabs. | Tabs include Sip Academy, Sipopedia, Flavor Wheel, Tasting Journal, Tasting Groups, Beverage Quiz, Beverage News, Regions. | Not Run
UAT-NAV-003 | Global Navigation | Ai RnD Sub-Nav | Guest/User | Brand tier set to Ai RnD | Functional | P2 | 1. Select Ai RnD tier. | News tab is available and selected state styling is applied. | Not Run
UAT-NAV-004 | Global Navigation | Somm Support Sub-Nav | Guest/User | Brand tier set to Somm Support | Functional | P2 | 1. Select Somm Support tier. | News tab is available and selected state styling is applied. | Not Run
UAT-NAV-005 | Global Navigation | Hash Routing - Supported Routes | Guest/User | Browser supports hash URLs | Functional | P1 | 1. Enter each supported hash route (Sip Academy, Sipopedia, Flavor Wheel, Tasting Journal, Tasting Groups, Beverage Quiz, Beverage News, Regions, Ai News, Somm News). | Each hash opens the intended page without full reload errors. | Not Run
UAT-NAV-006 | Global Navigation | Hash Alias Handling | Guest/User | App is loaded | Functional | P2 | 1. Navigate to #home. 2. Navigate to #terminology. | #home resolves to Sip Academy and #terminology resolves to Sipopedia. | Not Run
UAT-NAV-007 | Global Navigation | Invalid Hash Fallback | Guest/User | App is loaded | Functional | P1 | 1. Navigate to an unknown hash. | Application falls back to Sip Academy without crashing. | Not Run
UAT-NAV-008 | Global Navigation | Browser Back/Forward | Guest/User | Navigate across at least 3 tabs | Regression | P2 | 1. Move between multiple tabs and brand tiers. 2. Use browser back and forward. | Page state tracks browser history and updates content correctly. | Not Run
UAT-ACA-001 | Sip Academy | Auth Panel Render | Guest/User | Sip Academy tab open | UI | P2 | 1. Open Sip Academy. 2. Verify auth section visibility. | Auth panel is visible and actions are clearly available. | Not Run
UAT-ACA-002 | Sip Academy | AI Lab Prompt Flow | Guest/User | Sip Academy tab open | Functional | P1 | 1. Enter prompt in AI Lab. 2. Submit generation action. | User receives generated output or a clear non-breaking error state. | Not Run
UAT-ACA-003 | Sip Academy | Learning Path Node Navigation | Guest/User | Sip Academy tab open | Functional | P1 | 1. Open Learning Path. 2. Select current and unlocked nodes. | Lesson content panel updates to selected node and preserves active state. | Not Run
UAT-ACA-004 | Sip Academy | Lesson Modal Studio Open | Guest/User | An available lesson node exists | Functional | P1 | 1. Launch lesson studio/modal. 2. Close modal. | Modal opens with lesson content and closes without layout break. | Not Run
UAT-ACA-005 | Sip Academy | Interactive Mission Stepper | Guest/User | Sip Academy tab open | Functional | P2 | 1. In Interactive Mission, click Next and Back. | Step index and progress bar update correctly; boundary disabled states are correct. | Not Run
UAT-ACA-006 | Sip Academy | Premium Placeholder Block | Guest/User | Sip Academy tab open | UI | P3 | 1. Scroll to future premium section. | Premium section displays with locked disabled call-to-action. | Not Run
UAT-SIPO-001 | Sipopedia | Terminology Search | Guest/User | Sipopedia tab open | Functional | P1 | 1. Enter known term fragment in search input. | Results filter to matching terminology entries. | Not Run
UAT-SIPO-002 | Sipopedia | Bucket Filter | Guest/User | Sipopedia tab open | Functional | P1 | 1. Select an A-Z or # bucket. | Only entries in selected bucket are listed. | Not Run
UAT-SIPO-003 | Sipopedia | Pagination Controls | Guest/User | Result count exceeds page size | Functional | P2 | 1. Move to next and previous pages. | Page index updates and entries refresh correctly. | Not Run
UAT-SIPO-004 | Sipopedia | Page Size Selector | Guest/User | Sipopedia tab open | Functional | P2 | 1. Change page size value. | List density updates and pagination recalculates. | Not Run
UAT-SIPO-005 | Sipopedia | Term Detail Modal | Guest/User | At least one term listed | Functional | P1 | 1. Click a term row. 2. Review modal sections. 3. Close modal. | Modal shows term details and closes cleanly. | Not Run
UAT-SIPO-006 | Sipopedia | Outbound Reference Links | Guest/User | Term modal with links open | Functional | P3 | 1. Open an external reference link. | Link opens in a new tab or window. | Not Run
UAT-FLW-001 | Flavor Wheel | Beverage Tab Switching | Guest/User | Flavor Wheel tab open | Functional | P1 | 1. Switch among beverage tabs. | Wheel and detail panel update per selected beverage. | Not Run
UAT-FLW-002 | Flavor Wheel | Wheel Segment Selection | Guest/User | Flavor Wheel tab open | Functional | P1 | 1. Click multiple wheel descriptors segments. | Detail panel updates to selected descriptor family. | Not Run
UAT-FLW-003 | Flavor Wheel | Intensity Meters | Guest/User | Flavor Wheel tab open | UI | P2 | 1. Switch descriptor contexts. | Acidity and sweetness meters render with expected values styles. | Not Run
UAT-FLW-004 | Flavor Wheel | Fruit Reference Matrix | Guest/User | Flavor Wheel tab open | Functional | P2 | 1. Open Fruit Reference mode. 2. Select points in matrix. | Matrix interaction updates climate and fruit reference details. | Not Run
UAT-TJ-001 | Tasting Journal | Subtab Navigation | Guest/User | Tasting Journal tab open | Functional | P1 | 1. Switch across Make Notes, Review Notes, Analytics, Regions Map. | Each subtab loads corresponding panel without runtime errors. | Not Run
UAT-TJ-002 | Tasting Journal | Create Note | Guest/User | Tasting Journal Make Notes open | Functional | P1 | 1. Fill note fields. 2. Save note. | Note is saved and appears in Review list. | Not Run
UAT-TJ-003 | Tasting Journal | Blind Guess Scoring | Guest/User | Make Notes mode | Functional | P1 | 1. Enable blind mode. 2. Enter guesses and mark correctness. | Blind scoring controls and accuracy values update correctly. | Not Run
UAT-TJ-004 | Tasting Journal | Review Search and Select | Guest/User | At least two notes exist | Functional | P2 | 1. Search notes in review. 2. Select a note. | List filters and detail panel shows selected note. | Not Run
UAT-TJ-005 | Tasting Journal | Edit Existing Note | Guest/User | At least one note exists | Functional | P1 | 1. Open note in review. 2. Click Edit. 3. Update and save. | Updated values persist and are reflected in review. | Not Run
UAT-TJ-006 | Tasting Journal | Delete Note | Guest/User | At least one note exists | Functional | P1 | 1. Delete a note from review list. | Note is removed and analytics map counts update accordingly. | Not Run
UAT-TJ-007 | Tasting Journal | PDF Export | Guest/User | At least one note exists | Functional | P2 | 1. Select one or more notes. 2. Click Export PDF. | Printable document window opens with selected notes. | Not Run
UAT-TJ-008 | Tasting Journal | Analytics Calculations | Guest/User | At least three notes including blind entries | Functional | P1 | 1. Open Analytics tab. | Counts and accuracy recommendations reflect data. | Not Run
UAT-TJ-009 | Tasting Journal | Regions Map Interaction | Guest/User | At least one note with country | Functional | P2 | 1. Open Regions Map tab. 2. Click highlighted country. 3. Use search in directory. | Map selection filters directory and searchable list updates. | Not Run
UAT-TG-001 | Tasting Groups | Groups List and Detail Sync | Guest/User | Tasting Groups tab open | Functional | P1 | 1. Click different groups in sidebar list. | Main detail panel, meetup list, and feed preview sync to selected group. | Not Run
UAT-TG-002 | Tasting Groups | Search Fuzzy Location Alias | Guest/User | Tasting Groups tab open | Functional | P1 | 1. Search full state name for group stored as abbreviation. | Matching group appears even when state format differs. | Not Run
UAT-TG-003 | Tasting Groups | Focus Filter | Guest/User | Tasting Groups tab open | Functional | P2 | 1. Change Focus dropdown. | List updates to groups with selected focus type only. | Not Run
UAT-TG-004 | Tasting Groups | Create Group Mock | Guest/User | Tasting Groups tab open | Functional | P1 | 1. Fill Create Group form. 2. Submit. | New group appears in list and selection moves to created group. | Not Run
UAT-TG-005 | Tasting Groups | Map Pin City Filter | Guest/User | Tasting Groups map loaded | Functional | P1 | 1. Click a green city pin. | City filter activates and list is constrained to that city. | Not Run
UAT-TG-006 | Tasting Groups | Map Controls Fit Globe Zoom | Guest/User | Tasting Groups map loaded | Functional | P1 | 1. Click Fit. 2. Click Globe. 3. Use + and -. | Fit frames active groups, Globe shows world view, zoom adjusts viewport. | Not Run
UAT-TG-007 | Tasting Groups | Zoom Ceiling | Guest/User | Map loaded | Regression | P2 | 1. Zoom in repeatedly to max. | Maximum zoom reaches 600 percent and control disables at top bound. | Not Run
UAT-TG-008 | Tasting Groups | Pin Stroke Scaling | Guest/User | Map loaded | UI | P2 | 1. Compare pin and border sizes at Fit, Globe, high zoom. | Pins and strokes remain proportional and not oversized in fit mode. | Not Run
UAT-TG-009 | Tasting Groups | Enhanced Detail Layer Fallback | Guest/User | Map loaded and zoom at least 135 percent | Functional | P3 | 1. Zoom above detail threshold. | If detail layers fail, base map still works and fallback message is shown. | Not Run
UAT-BQ-001 | Beverage Quiz | Quiz Generation | Guest/User | Beverage Quiz tab open | Functional | P1 | 1. Select beverage and options. 2. Generate quiz. | Question set is generated and shown with options. | Not Run
UAT-BQ-002 | Beverage Quiz | Answer Selection | Guest/User | Quiz generated | Functional | P1 | 1. Select answers for multiple questions. | Selections persist and current choices are highlighted. | Not Run
UAT-BQ-003 | Beverage Quiz | Scoring and Reveal | Guest/User | Quiz answered | Functional | P1 | 1. Submit score. 2. Reveal answers or explanations. | Score and correctness indicators display accurately. | Not Run
UAT-BQ-004 | Beverage Quiz | Printable Quiz Export | Guest/User | Quiz generated | Functional | P2 | 1. Use printable export action. | Printable window PDF flow opens with quiz details. | Not Run
UAT-BQ-005 | Beverage Quiz | Email Share Draft | Guest/User | Quiz complete | Functional | P3 | 1. Enter recipient email and trigger share flow. | Share flow validates input and prepares output without errors. | Not Run
UAT-BN-001 | Beverage News | News Load and Refresh | Guest/User | Beverage News tab open | Functional | P1 | 1. Load page. 2. Trigger refresh. | News cards load and refresh action updates stable UI states. | Not Run
UAT-BN-002 | Beverage News | Source Category Filters | Guest/User | News loaded | Functional | P1 | 1. Toggle category chips. | Cards are filtered by selected source categories. | Not Run
UAT-BN-003 | Beverage News | Per Source Toggles | Guest/User | News loaded | Functional | P2 | 1. Enable disable specific source chips. | Result list updates to source inclusion exclusion. | Not Run
UAT-BN-004 | Beverage News | Pagination | Guest/User | News results exceed one page | Functional | P2 | 1. Move between pages. | Pagination updates page index and cards correctly. | Not Run
UAT-BN-005 | Beverage News | Card Outbound Links | Guest/User | News cards visible | Functional | P3 | 1. Open a news source or article link. | Link opens target content in new tab or window. | Not Run
UAT-REG-001 | Regions | Continent Jump Navigation | Guest/User | Regions tab open | Functional | P1 | 1. Click continent jump chips. | Page jumps to corresponding continent section. | Not Run
UAT-REG-002 | Regions | Country Card to Detail | Guest/User | Regions list visible | Functional | P1 | 1. Open a country from regions list. | Country detail route opens with hero and structured sections. | Not Run
UAT-REG-003 | Regions | Country Carousel | Guest/User | Country detail page open | Functional | P2 | 1. Use region carousel controls. | Carousel changes slides with updated caption and metadata. | Not Run
UAT-REG-004 | Regions | Resource Links | Guest/User | Country detail page with links | Functional | P3 | 1. Open listed resource links. | External resources open correctly. | Not Run
UAT-REG-005 | Regions | Invalid Region Slug State | Guest/User | App loaded | Regression | P2 | 1. Navigate to hash regions nonexistent country. | User sees controlled not found state with ability to navigate back. | Not Run
UAT-AIRND-001 | Ai RnD | AI News Cards | Guest/User | Brand tier set to Ai RnD | UI | P2 | 1. Open Ai RnD News. | Curated source cards render with category tag summary and CTA. | Not Run
UAT-AIRND-002 | Ai RnD | External Source Open | Guest/User | Ai RnD cards visible | Functional | P3 | 1. Click Open Source on multiple cards. | Each destination opens correctly in new tab or window. | Not Run
UAT-SOMM-001 | Somm Support | News Impact Cards | Guest/User | Brand tier set to Somm Support | UI | P2 | 1. Open Somm Support News. | Impact highlight and placeholder community cards render. | Not Run
UAT-SOMM-002 | Somm Support | Placeholder Link Labels | Guest/User | Somm Support News open | Regression | P3 | 1. Review community link cards. | Cards show placeholder text indicating links are not connected. | Not Run
UAT-CROSS-001 | Cross-Cutting | Desktop Layout | Guest/User | Desktop viewport | UI | P1 | 1. Navigate each major tab at desktop width. | Cards grids and controls are aligned with no overflow. | Not Run
UAT-CROSS-002 | Cross-Cutting | Tablet Mobile Responsiveness | Guest/User | Tablet or mobile viewport | UI | P1 | 1. Repeat core interactions at 980px and 760px breakpoints. | Layouts collapse correctly and remain usable. | Not Run
UAT-CROSS-003 | Cross-Cutting | Keyboard Focus Visibility | Guest/User | Any page | Accessibility | P2 | 1. Navigate controls with Tab and Shift Tab. | Visible focus indicators are present and order is sensible. | Not Run
UAT-CROSS-004 | Cross-Cutting | Basic Error Resilience | Guest/User | Attempt network dependent actions | Regression | P1 | 1. Trigger actions that can fail such as refresh or generation. | UI shows informative notice states without crashing. | Not Run

## Coverage Matrix
Area | Total | Pass | Fail | Blocked | Not Run | Pass Rate
Ai RnD
Beverage News
Beverage Quiz
Cross-Cutting
Flavor Wheel
Global Navigation
Regions
Sip Academy
Sipopedia
Somm Support
Tasting Groups
Tasting Journal
TOTAL